## Timeline
2014-05-24 | 2014-06-04 | 2014-06-08 | 2014-06-22 | 2014-06-29 | 2014-07-06 | 2014-07-19 | 2014-07-25 | 2014-07-31 | 2014-08-01
Complete dataserver code
Complete all test cases
Complete front end /back end web
Complete Android app
Complete badge system and UI for web and android
Notes:
- Testcases must be done after a project is completed, such as dataserver project. Please don't wait everything done to do testcases.
- The works must be done before or at the day in schedule, not the time to start.
- If you see that the schedule is too tight or loose, please no hesitate to inform me.
REAL LIFE REAL GAME SCHEDULE
Deploy and testing on server
Release
Test and fix bugs
PR on all possible channels

## Project Plan
RLRG Project plan |  |  |  |  | To be completed by: | Thắng PN
[5 empty] | Deadline: | Date
Done? | Data project | Due By | Assignee | Notes
a | Paperwork | 2014-05-11 | Thắng PN | Write project requirements
a | Json Library | 2014-05-24 | Thắng PN | Write json writer/reader library
a | Project Preparation | 2014-05-08 | Thắng PN | Initialize all required projects
a | Lang/PBL module | 2014-05-31 | Thắng PN | Write webservices to handle datas in both ways: request and response
a | Profile module | 2014-05-31 | Thắng PN | Write webservices to handle datas in both ways: request and response
a | Task module | 2014-05-31 | Thắng PN | Write webservices to handle datas in both ways: request and response
| Unittest For modules | 2014-06-04 | Thắng PN | Write unittest to make sure there webservices is work well. Beside that, please ensure the performance as well.
| Test case | 2014-06-08 | Ngọc Ánh | Write test cases to test data server
| Testing | 2014-06-14 | Nam Lê + Thắng PN | Test data server bases on testcases.
| Deploy | 2014-06-15 | Thắng PN | Deploy data server on testing server.
a | Write data test | 2014-05-31 | Thắng PN | Write data for testing
Done? | Web project | Due By | Assignee | Notes
| Paperwork | 2014-06-01 | Thắng PN | Write project requirements
| Preparation | 2014-06-07 | Anh Đ | Initialize project on php/java and related stuffs
| Front-end web | 2014-06-22 | Anh Đ | Write entire front-end web for users bases on php language
| Back-end web | 2014-06-22 | Phương T + Thắng PN | Write entire back-end web for users bases on java language
| Unittest for webs | 2014-06-29 | Anh Đ + Phương T | Write unittests for both websites. Write unittests as the time you implemented will greatly help.
| Test case | 2014-07-06 | Nam Lê | Write test cases for both front/back end websites.
| Testing | 2014-07-19 | Nam Lê + Phương T + Thắng PN | Test websites bases on testcases.
Done? | Android project | Due By | Assignee | Notes
| Paperwork | 2014-06-01 | Thắng PN | Write project requirements
a | Preparation | 2014-06-24 | Nghiêm Lê | Initialize android project and related stuffs
| Design UI | 2014-06-08 | Nghiêm Lê | Design UI bases on the designs of designer
| Coding | 2014-06-22 | Nghiêm Lê + Phương T | Code project bases on requirements
| Unitest for android | 2014-06-22 | Nghiêm Lê + Phương T | Write unittests for android. Write unittests as the time you implemented will greatly help.
| Test case | 2014-06-29 | Nam Lê | Write test cases for android project
| Testing | 2014-07-06 | All members | Because the app on smartphone is more important than on website, please be sure it works well.
Done? | Design UI | Due By | Assignee | Notes
| Paperwork | 2014-05-31 | Thắng PN | Write design requirements
| Preparation | 2014-06-24 | Nguyen San | Initialize designs and related stuffs
| Design UI for Android | 2014-06-08 | Nguyen San | Design UI bases on requirements
| Design UI for both websites | 2014-06-22 | Nguyen San | Design UI bases on requirements
| Design badge system | 2014-06-22 | Nguyen San | Design badges bases on badges list
Done? | Psychology design | Due By | Assignee | Notes
| Paperwork | 2014-05-01 | Thắng PN | Write design requirements
| Preparation | 2014-05-25 | Diệu Ly | Initialize designs and related stuffs
| Meeting to design UI and colors | 2014-05-27 | Diệu Ly
| Design categories for task | 2014-06-01 | Diệu Ly | Design UI bases on requirements
| Design badges system | 2014-06-15 | Diệu Ly + All members | Design badges bases on badges list
| Design messages for badge system | 2014-06-22 | Diệu Ly + All members | Design message for badges
| Calculate the balance feature | 2014-06-22 | Thắng PN + Diệu Ly | Calculate algorithm for the balance feature
Done? | Other works | Due By | Assignee | Notes
| Design logging and store user's activites | 2014-06-01 | Thắng PN | We have to log user's actitvies to improve the app on later version.
| Prepare testing server | 2014-06-12 | Thắng PN
Notes:
- Please review all the plans to make sure we can do it.
- Don't hesitate to feedback to me about worktime, I have to manage the time we release to inform to the mentors.